## Tabellenblatt1
WP overview
WP Nr | Scope | In Charge
WP1 | Person or entity for privacy policy and imprint // No one yet in the future an association | ??
Wp2 | Collecting all Content (wp2) // Same as wp9? And if approaching the people in charge then maybe wp6 (confirmed venues) and wp7 (agenda – meetups / speakers) and wp8 (getting all the eventbrite links) | Maya and Lesa
WP3 | Basic web layout / well all graphical work out of the box Carlos solution | Olga and Chris
WP4 | Building the sites following the design and using CSS and HTML (Front-end development) | Ben is asking his team everyone should ask their network
WP5 | Point the blockchainweek.berlin to the github repository | Christopher
WP6 | Venues: Collection all confirmed locations | Maya & Lesa
WP7 | Each venue pocs should ask for meetups / agenda | Maya & Lesa
WP8 | Each meetup organizer needs to give us the link to their Eventbrite meetup signup for that event and we need to collect these | Maya & Lesa
WP9 | Collecting all the needed content Merge with wp2? It is the same.. | Maya & Lesa
WP10 | Coordination of all the workpackages and weekly status report | Daud
Wp11 | Not too sure – no design my fault till now // Always stated it needs to be collaborative work | Daud / Fauve? / Lesa? / Anna?
WP12 NEW! | GitHub Accout that is hosting the web | Carlos
Decisions made today
We get together next week in Berlin
We don't wait any longer and discuss not but execute
We do it among the contributors
We need to find the CSS / React / GIT guy or gal that does the design
We want to launch asap because of the press & marketing means
We first ask Olga and Chris when they contribute and if they can't do it asap then we need to check for other design ressources and use what they have done so far
The website code will stay on Carlos Github repository